# Community CVS Information Sheet

## B10  PROJECT PLANNING

#### There are several key steps in planning a project

- Identifying Need

- Providing a Reasonable Response to this Need

- Defining aims, outputs and outcomes

- Planning Resource Requirement

- Costing the Resource Requirements - Budget

- Planning Monitoring and Evaluation

- IDENTIFYING NEED

This is your starting point, you need to identify a need and plan a project which meets that need.  But, how do you know there is a need for your project?

When you are planning a project you must provide evidence that there is a need, and there are a number of ways to do this;

Statistics – health, crime, education, data, population, trends, unemployment

Experience – information you have recorded whilst providing your existing service, current usage, profile of users e.g.) age, location, whether you are able to meet current demand

Consultation – do other people also agree that there is a need, discuss and consult with users of your service, you can use public meetings, or questionnaires, informal feedback or focus groups.

Similar Services – is anyone else providing a service which would meet the need you have identified?  Talk to statutory agencies like the local council, Health and Education if relevant and other voluntary groups.  If the need is already being met, do not try to duplicate the service, look at ways of complimenting existing service provision.

- PROVIDING A REASONABLE RESPONSE TO THIS NEED

Your project must have a sensible and realistic project plan.  It should fit in with your other activities and experience.  It should be achievable and respond to the need you have identified.  When you are planning your project, be realistic about your expertise and skills and the ability of your group to manage the project.

Company Registration No:  3530868

Charity No:  1070612

- DEFINING AIMS, OUTPUTS AND OUTCOMES

Your project must have clear aims and objectives, which clearly state what your project will achieve and what difference it would make. Your objectives should be “SMART”

Specific

Measurable

Achievable

Reviewable

Time

(Decide how you will deliver the project e.g.)

Buying equipment and using it

Employing a worker

Setting up an office or project base

Refurbishing a building

Setting up training courses

Providing specific services and activities e.g.) advice service or crèche

- PLANNING RESURCE REQUIREMENTS

The sorts of resources you may need to include:

Premises – rent, refurbishment

Staff and volunteers

Equipment – furniture, computer, telephones

Running costs – postage, stationery, insurance

Training budget

Publicity

- COSTING THE RESOURCE REQUIREMENTS - BUDGET

Your project budget should show that all elements of the project have been costed accurately.  The budget should be a cost-effective way of delivering the project.  You can use a range of sources to get costs, including quotes, stationery catalogues, specialist firms, other voluntary and statutory organisations for pay scales and cost of floor space per foot etc.

- PLANNING MONITORING AND EVALUATION

Plan how you will monitor or record your achievements using statistics and other quality measures.  If you have clear objectives you should be able to monitor how well you have met these.  Show how you will evaluate your project, how you will identify successes and problem areas and learn from this and use it to inform future plans.

For more information on Project Planning visit http://www.communitycvs.org.uk/

Acknowledgement for information in this leaflet is to the Community Fund Project Planning Workshop – Information Conference 2001.